## Decision Log
Decision Log
REF | Date raised | Source | Description | Proposed | Seconded | Outcome | Final Decision | Update | Next Steps | Date closed
D01 | 2026-07-10 | Radcliffe PiPP Board Meeting | The Board raised issue with the value for money of consultancy support. | Christian Wakeford MP | James Frith MP | Board agreed unanimously | The Board agreed unanimously to pause further consultancy work pending receipt of: • Full engagement findings • Qualitative consultation data • Revised Phase 2 guidance from MHCLG | Feedback workshop undertaken with consultants on 12/08/2026 to discuss consultantion and enagagement findings. Full report issued to the Board following the workshop. Bury Council drafted Deed of Variation and issued to Constellia for pausing contract with Hive Consultancy. | Board to discuss the findings of the report and feedback any comments to Placed, the consultants, by 01/09/2026. Bury Council/ Constellia to issue Deed of Variation to pause the contract with the consultants. PiPP Board to determine position by 01/09/2026 to either utilise the consultants for the remainder of the contract (to develop the 10-year plan) or terminate contract.
D02 | 2026-07-10 | Radcliffe PiPP Board Meeting | The Board discussed support arrangements and costs provided by Bury VCFA to undertake required duties. | N/A | N/A | Board agreed unanimously | The Board agreed to defer a decision on future support arrangements pending receipt of full cost comparisons and governance information. Decisions may be made electronically between meetings if required due to timescales. | Bury Council provided a comparison for the role and an associated cost. After comparing the quotes from Bury VCFA and Bury Council the PiPP Board decided to appoint the VCFA to undertake required duties associated with the Board. | Contract to be developed to appoint Bury VCFA for the required services. See D07. | 2026-08-03
D03 | 2026-07-10 | Radcliffe PiPP Board Meeting | Proposed that Outwood Country Park be included within the Pride in Place boundary area to support future opportunities around walking, cycling, health, wellbeing and environmental improvements. | Cllr. Mike Smith | Christian Wakeford MP | Board agreed unanimously | That Outwood Country Park be included within the Pride in Place boundary area to support future opportunities around walking, cycling, health, wellbeing and environmental improvements. | Revised boundary line submitted to MHCLG for formal consideration. Awaiting feedback as to whetehr revised boundary line has been accepted.
D04 | 2026-07-10 | Radcliffe PiPP Board Meeting | Chair invited nominations for the position of Vice Chair. | Clare Standish | Cllr. Mike Smith | Board agreed unanimously | The Board agreed unanimously agreed Clare Standish as Vice Chair for an initial one-year term. | N/A | N/A | 2026-07-10
D05 | 2026-07-10 | Radcliffe PiPP Board Meeting | Decision making processes. | N/A | N/A | Board agreed unanimously | The Board agreed unanimously that urgent decisions can be made electronically via email between meetings where timescales require this. | N/A | N/A | 2026-07-10
D06 | 2026-07-10 | Radcliffe PiPP Board Meeting | Radcliffe PiPP Terms of Reference | N/A | N/A | Board agreed unanimously | Revised Terms of Reference approved in principle, subject to the agreed amendments and final circulation. | TOR ammended, circulated and updated to the PiPP webpages. | N/A | 2026-07-24
D07 | 2026-08-03 | Radcliffe PiPP Board (Virtual Discussion) | Formal decision to appoint Bury VCFA to the role of secretariat and any other functions required by the Board. | N/A | N/A | Majority agreement form Board | Appoint Bury VCFA to the role of secretariat and any other functions required by the Board. Contracts to be drawn up.