## Decision Log
Decision Log
REF | Date raised | Source | Description | Proposed | Seconded | Outcome | Final Decision | Update | Next Steps | Date closed
D01 | 2026-07-10 | Radcliffe PiPP Board Meeting | The Board raised issue with the value for money of consultancy support. | Christian Wakeford MP | James Frith MP | Board agreed unanimously | The Board agreed unanimously to pause further consultancy work pending receipt of: • Full engagement findings • Qualitative consultation data • Revised Phase 2 guidance from MHCLG
D02 | 2026-07-10 | Radcliffe PiPP Board Meeting | The Board discussed support arrangements and costs provided by Bury VCFA to undertake required duties. | N/A | N/A | Board agreed unanimously | The Board agreed to defer a decision on future support arrangements pending receipt of full cost comparisons and governance information. Decisions may be made electronically between meetings if required due to timescales.
D03 | 2026-07-10 | Radcliffe PiPP Board Meeting | Proposed that Outwood Country Park be included within the Pride in Place boundary area to support future opportunities around walking, cycling, health, wellbeing and environmental improvements. | Cllr. Mike Smith | Christian Wakeford MP | Board agreed unanimously | That Outwood Country Park be included within the Pride in Place boundary area to support future opportunities around walking, cycling, health, wellbeing and environmental improvements.
D04 | 2026-07-10 | Radcliffe PiPP Board Meeting | Chair invited nominations for the position of Vice Chair. | Clare Standish | Cllr. Mike Smith | Board agreed unanimously | The Board agreed unanimously agreed Clare Standish as Vice Chair for an initial one-year term.
D05 | 2026-07-10 | Radcliffe PiPP Board Meeting | Decision making processes. | N/A | N/A | Board agreed unanimously | The Board agreed unanimously that urgent decisions can be made electronically via email between meetings where timescales require this.
D06 | 2026-07-10 | Radcliffe PiPP Board Meeting | Radcliffe PiPP Terms of Reference | N/A | N/A | Board agreed unanimously | Revised Terms of Reference approved in principle, subject to the agreed amendments and final circulation.